## Sheet1
MAIN PORTAL AND API
USER STORY | STORY POINTS | SPRINT/ITERATION
As an end user I need to register my vehicles So that I can be the registered owner of my vehilcle | 1 | 1
As a product owner I need to provide basic vehicle data so that they can be visible on demand | 1 | 5
As a product owner I need to secure authentication so that we can establish the identity of the owner | 3 | 1
As a product owner I need to create and register a fleet of cars so that I can provide service to B2B customer | 2 | 5
As a product owner I want to create and register a fleet of bike so that I can provide service to B2B customer | 2 | 5
As a product owner I need to create and register a fleet of truck so that I can provide service to B2B customer | 1 | 5
As a product owner I need to intregrate payment gateway so that I can provide value added services | 2 | 1
As a Product owner I want the integration of vehicle registry databases in Asia so that I can gather basic information | 3 | 3
As a Product owner I want the integration of vehicle registry databases in Europe so that I can gather basic information | 3 | 4
As a Product owner I want the integration of vehicle registry databases in Africa so that I can gather basic information | 3 | 4
As a Product owner I want the integration of vehicle registry databases in Australia so that I can gather basic information | 4 | 4
As a Product owner I want the integration of vehicle registry databases in North America so that I can gather basic information | 4 | 3
As a Product owner I want the integration of vehicle registry databases in South America so that I can gather basic information | 4 | 3
As a Product owner I want the integration of vehicle insurer databases so that insurance claim information is gathered. | 2 | 4
As a Product owner I want extensible data store so that data from the vehicle systems is captured. | 5 | 1
As a Product owner I want integration with an analytics platform so that analytic services can be provided to the customers. | 2 | 3
As a Product owner I want REST based API so that third party access can be enabled. | 2 | 2
As a Product owner I want REST based API so that home-built apps access can be enabled. | 1 | 2
As an end user I want an iOS app so that services are available to iOS users. | 3 | 2
As an end user I want an Android app so that services are available to Android users. | 5 | 2
As an end user I want an Blackberry app so that services are available to Blackberry users. | 3 | 5
As an end user I want a Windows app so that services are available to Windows users. | 3 | 5